## General information about TPCE
Background on why TPCE are needed
MnDOT requires a TPCE as soon as the project is included in a MnDOT plan or the program. It should be entered into CHIMES at that time. The CHIMES Total Project Cost Estimate is MnDOT’s authoritative source for maintaining and talking about TPCE. The information shown in the project data TPCE section is the responsibility of the project manager before letting, and construction resident engineer after letting. The engineer responsible for the estimates may delegate entry of this information to another user, but is still responsible for the accuracy of the entered information.
The TPCE is also required to meet the requirements for MN Statutes 174.56, This statue requires a report by Dec. 15 every year for projects with a TPCE $15M Metro and $5M non metro. The report is to include not only projects in preletting but ones that are in construction up to 6 months of substantial completion
https://www.revisor.mn.gov/statutes/cite/174.56
Subd. 2a. The report most containt the total expenditures from the trunk highway fund during the previous fiscal year in the following categories: road construction; planning; design and engineering; labor; compliance with environmental regulations; administration; acquisition of right-of-way, including costs for attorney fees and other compensation for property owners; litigation costs, including payment of claims, settlements, and judgments; maintenance; and road operations.
Once the project has been let, you can look in CHIMES to see what has been spent already and update the TPCE. The actual Total Project Cost shown in chimes, is what has already been spent and comes in from the SWIFT expenditures, this shows up in chimes in the TPCE area of the screen as “Committed” values. Committed values are calculated by combining SWIFT encumbrances and expenditures for display in CHIMES.

## TPCE
TOTAL PROJECT COST ESTIMATE (TPCE) DESIGN-BID-BUILD | [13 empty] | fill in blue
Project Information | SP : | 3604-80 | Trunk Highway: | 11 |  | Estimate's Completion Date: | 2023-07-31 |  | CONSTRUCTION START DATE (MM/DD/YYYY) |  | 2024-05-01 | FY 2024 |  | pull down selection in darker blue
| District : | 2 | Prime Element ID : |  | TPCE Stage: |  | FY of Letting: | 2024 | CONSTRUCTION END DATE |  | 2024-10-01 | FY 2025
| Project Length: | 1.12 Miles | Project Description: (Scope & Location) | This project will consist of a road realignment and replacement of roadside infrastructure within the project limits. |  |  | Budget Level: | 3 | CHIMES INFLATION |  | 1.06
DIVISION | GROUP (I) | CATEGORY (II) | DETAILS (III) | % | BASE ESTIMATE (IV) | CONTINGENCY (V) OR Risk (Choose Largest) | TOTAL (VI) | FY OF LETTING (INFLATED) (VII) | FY of Letting (Inflated) split between local/Non MnDOT and MnDOT |  |  |  | INFLATED ROUNDED AMOUNT (VIII) |  |  | Rounding rules applied to construction costs:
[9 empty] | MNDOT FUNDS |  | LOCAL FUNDS |  |  |  |  | i. For projects under $1,000,000, round to the next $10,000. (i.e. – a $156,123.86 project would round to $160,000). ii. For projects $1,000,000 to $100,000,000, round to the next $100,000. (i.e. – a $1,509,000 project would round to $1,600,000 and a $12,772,000 project would round to $12,800,000). iii. For projects greater than $100 million, round to the next million. (i.e. – a $300,500,000 project would round to $301,000,000).
[9 empty] | % |  | %
Construction Contract | CONSTRUCTION_LET_AMOUNT
Investment Groups
| Asset Management - Pavement |  |  | 73.49% | 2206996 |  | 2206996 | 2339415.76 | 100% | 2339415.76 | 0% | 0
| Asset Management - Bridge |  |  | 0% |  |  | 0 | 0 | 100% | 0 | 0% | 0
| Asset Management - Roadside Infrastructure |  |  | 21.42% | 643319 |  | 643319 | 681918.14 | 100% | 681918.14 | 0% | 0
| Asset Management - Guardrail |  |  | 0% |  |  | 0 | 0 | 100% | 0 | 0% | 0
| Traveler Safety |  |  | 5.083% | 152636 |  | 152636 | 161794.16 | 100% | 161794.16 | 0% | 0
| Critical Connections - Bicycle Infrastructure |  |  | 0% |  |  | 0 | 0 | 100% | 0 | 0% | 0
| Critical Connections - Acc. Ped. Infrastructure |  |  | 0% |  |  | 0 | 0 | 100% | 0 | 0% | 0
| Risk Register | [5 empty] | 0 | 0 | 100% | 0 | 0% | 0
| 1. Project Cost Estimate at time of letting, Construction Contract Items Only ( Today's Dollars ) |  |  |  | 3002951 | 0 | 3002951 | 3183128.06 | 3183128.06 |  | 0 |  | 3200000 |  | [A]
| POST_LETTING_CON_COSTS | [5 empty] | 0 | 0 | 100% | 0 | 0% | 0
| SA/Overruns |  |  |  | 120118.04 |  | 120118.04 | 127325.1224 | 100% | 127325.1224 | 0% | 0
| Incentives |  |  |  | 45044.265 |  | 45044.265 | 47746.9209 | 100% | 47746.9209 | 0% | 0
[7 empty] | 0 | 0 | 100% | 0 | 0% | 0
[7 empty] | 0 | 0 | 100% | 0 | 0% | 0
| 2. Project Cost Estimate after letting, Construction Contract Items Only ( Today's Dollars ) |  |  |  | 165162.305 | 0 | 165162.305 | 175072.0433 | 175072.0433 |  | 0 |  | 180000 |  | [B]
Total Construction Contract Amount |  |  |  |  | 3168113.305 | 0 | 3168113.305 | 3358200.1033 | 0 |  | 0 |  | 3380000
Other Project Costs | OTHER_PROJECT_COSTS | [5 empty] | 0 | 0 |  | 0 | 100% | 0
[7 empty] | 0 | 0 |  | 0 | 100% | 0
| Agreements | [5 empty] | 0 | 0 |  | 0 | 100% | 0
| Utilities | [5 empty] | 0 | 0 |  | 0 | 100% | 0
| Municipal/Local Issues | [5 empty] | 0 | 0 |  | 0 | 100% | 0
| Railroad | [5 empty] | 0 | 0 |  | 0 | 100% | 0
| Environmental Mitigation | [5 empty] | 0 | 0 |  | 0 | 100% | 0
| Environmental Cleanup | [5 empty] | 0 | 0 |  | 0 | 100% | 0
| Pre-Letting Traffic Mgmt. | [5 empty] | 0 | 0 |  | 0 | 100% | 0
[7 empty] | 0 | 0 |  | 0 | 100% | 0
| Preconstruction Cost (C) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| OTHER_PROJECT_COSTS | [5 empty] | 0 | 0 |  | 0 | 100% | 0
[7 empty] | 0 | 0 |  | 0 | 100% | 0
| Construction Traffic Mgmt. | [5 empty] | 0 | 0 |  | 0 | 100% | 0
[7 empty] | 0 | 0 |  | 0 | 100% | 0
| Detours and Haul Roads | [5 empty] | 0 | 0 |  | 0 | 100% | 0
[7 empty] | 0 | 0 |  | 0 | 100% | 0
| During Construction Cost (D) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OTHER_PROJECT_COSTS | [5 empty] | 0 | 0 |  | 0 | 100% | 0
[7 empty] | 0 | 0 |  | 0 | 100% | 0
| Turn Backs | [5 empty] | 0 | 0 |  | 0 | 100% | 0
| Landscaping | [5 empty] | 0 | 0 |  | 0 | 100% | 0
| Mitigation | [5 empty] | 0 | 0 |  | 0 | 100% | 0
| Aesthetics | [5 empty] | 0 | 0 |  | 0 | 100% | 0
[7 empty] | 0 | 0 |  | 0 | 100% | 0
[7 empty] | 0 | 0 |  | 0 | 100% | 0
| Post Construction Cost (E) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3. Other Project Costs (C+D+E) (Not in Main contract, Not engineering or ROW) |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | [C]
Total Construction Costs |  |  |  | 3168113.305 | 0 | 3168113.305 | 3358200.1033 | 3358200.1033 |  | 0 |  | 3380000
DIVISION | GROUP (I) | CATEGORY (II) | DETAILS (III) | BASE ESTIMATE (IV) | CONTINGENCY (V) OR Risk (Choose Largest) | TOTAL (VI) | FY OF LETTING (INFLATED) (VII) | FY of Letting (Inflated) split between local/Non MnDOT and MnDOT |  |  |  | INFLATED ROUNDED AMOUNT (VIII) |  |  | Rounding rules applied to Engineering costs:
[8 empty] | MNDOT FUNDS |  | LOCAL FUNDS |  |  |  |  | i. For projects under $300,000, round up to the next $10,000 ii. For projects over $300,000, round up to the next $100,000.
[8 empty] | % |  | %
Engineering | PRELIMINARY_ENGINEERING |  | internal or external
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
| Internal at 12% |  |  | 360354.12 |  | 360354.12 | 381975.3672 |  | 0 | 100% | 381975.3672
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
| 4.Preliminary Engineering Total |  |  | 360354.12 | 0 | 360354.12 | 381975.3672 | 0 |  | 381975.3672 |  | 400000 |  | [D] | last resort use rule of thumb if you don't have a TTAA or a good estimate is 12% of construction costs
| CONSTRUCTION_ENGINEERING |  | internal or external
[6 empty] | 0 | 0 |  | 0 | 100% | 0
| Internal at 18% |  |  | 540531.18 |  | 540531.18 | 572963.0508 |  | 0 | 100% | 572963.0508
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
| 5.Construction Engineering Total |  |  | 540531.18 | 0 | 540531.18 | 572963.0508 | 0 |  | 572963.0508 |  | 600000 |  | [E] | last resort use rule of thumb if you don't have a better estimate is 8% of construction costs
Total Engineering Costs |  |  |  | 900885.3 | 0 | 900885.3 | 954938.418 | 0 |  | 954938.418 |  | 1000000
Right of Way | GROUP (I) | CATEGORY (II) | DETAILS (III) | BASE ESTIMATE (IV) | CONTINGENCY (V) OR Risk (Choose Largest) | TOTAL (VI) | FY OF LETTING Do not apply inflation due to the fact that the R/W estimate already applied market conditions in its calculation. (VII) | FY of Letting split between local/Non MnDOT and MnDOT |  |  |  | INFLATED ROUNDED AMOUNT (VIII) |  |  | No rounding rules have been applied to ROW costs:
[8 empty] | MNDOT FUNDS |  | LOCAL FUNDS |  |  |  |  | For costs, communicate with the District R/W engineer/manager for the cost estimates and whether or not they have rounded the R/W cost provided. If Right of Way rounding is not transferred from the R/W cost sheet, the rounding will need be consistent with the OLM rounding rules in the R/W cost estimate tool.
[8 empty] | % |  | %
[6 empty] | 0 |  | 100% | 0 | 0% | 0
|  | Standard Real Estate Purchase - Partial Take |  | 40000 |  | 40000 |  | 100% | 40000 | 0% | 0
[6 empty] | 0 |  | 100% | 0 | 0% | 0
[6 empty] | 0 |  | 100% | 0 | 0% | 0
[6 empty] | 0 |  | 100% | 0 | 0% | 0
|  | ROW Labor | internal | 100000 |  | 100000 |  | 100% | 100000 | 0% | 0
|  | ROW Labor | external |  |  | 0 |  | 100% | 0 | 0% | 0 |  |  |  | last resort if you don't have a better estimate and contract, ROW engineering rule of thumb is 12% of ROW costs
| 6. Total Right of Way Costs (including labor/engineering) |  |  | 140000 | 0 | 140000 | 0 | 140000 |  | 0 |  | 140000 |  | [F]
Total ROW Costs ( INCLUDING ROW LABOR COSTS ) |  |  |  | 140000 | 0 | 140000 | 0 | 140000 |  | 0 |  | 140000
DIVISION | GROUP (I) | CATEGORY (II) | DETAILS (III) | BASE ESTIMATE (IV) | CONTINGENCY (V) OR Risk (Choose Largest) | TOTAL (VI) | FY OF LETTING (INFLATED) (VII)
Partner Funding | PARTNER_FUNDING |  |  |  |  | 0 | 0
Total Partner Funding ( These costs are not included elsewhere on this sheet, it is only for funds that do not go through chimes. Very few projects will have anything entered here. ) |  |  |  | 0 | 0 | 0 | 0 | [G]
PROJECT TOTAL |  |  |  | Total Base Cost | Total Contingency | Total cost | Total inflated Cost | Total inflated cost rounded cost
TPCE, this includes Partner funding |  |  |  | 4208998.605 | 0 | 4208998.605 | 4313138.5213 | 4520000
Total Budget, this goes through chimes and does not include Partner funding |  |  |  | 4208998.605 | 0 | 4208998.605 | 4313138.5213 | 4520000
Estimator: |  |  |  | Approval By:
Project Manager: |  |  |  | Print Name:
Title:
Date:
Note on B35: Bridget Miller: For TH projects only. Other Elements are for agreements that support the construction phase of the project and are for work not included in the construction contract. See pull down menu tab for examples
Note on C11: Bridget Miller: for TH projects, this is updated to show the amounts of the annual estimate. Upon award of the construction contract, the latest estimate is replaced with the construction contract award amount.
Note on C27: Bridget Miller: For TH projects only. Includes any changes to the initial construction contract award amount.
Note on C74: Bridget Miller: cost incurred to get project ready for construction, through project award/award encumbrance date, this includes salaries, consultants, equipment used, materials to do the engineering
Note on C91: Bridget Miller: all engineering and oversight costs incurred during the construction phase of a project, from the date of award/award encumbrance through final project closeout, including internal salary, consultants equipment used in the field, materials needed to do engineering
Note on G71: Amount based on Expected Value (Risk Assessment) [PxI]
Note on G100: Amount based on Expected Value (Risk Assessment) [PxI]
Note on G114: Amount based on Expected Value (Risk Assessment) [PxI]
Note on H8: Amount based on Expected Value (Risk Assessment) [PxI]
Note on I25: If the letting was today, this would be the cost.
Note on I32: If the letting was today, this would be the cost.
Note on J25: This is the estimated bid amount for the future scheduled letting date. This number includes inflation.
Note on J32: This is the estimated bid amount for the future scheduled letting date. This number includes inflation.
Note on L110: Bridget Miller: If using ROW from your ROW engineer estimating tool, put the rounded cost information here to overwrite calculations. ROW is rounded differently
Note on M3: Bridget Miller: Month/Date/Year
Note on M4: Bridget Miller: Month/Date/Year
Note on N89: Bridget Miller Rule of thumb is 12% construction cost
Note on N96: Bridget Miller: Rule of thumb is 8%
Note on N110: Bridget Miller: Need to fill in, see yellow note above

## CHIMES INFLATION
Cost Estimate Inflation Conversion Factor Table
Historical/Current Baseline Fiscal Year ↓ | Future Projection Fiscal Year
| 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033
YOY D% | 13% | 4% | 1% | 2% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4%
2017 | 1.48 | 1.53 | 1.55 | 1.58 | 1.63 | 1.69 | 1.76 | 1.83 | 1.9 | 1.98 | 2.06 | 2.14
2018 | 1.28 | 1.33 | 1.35 | 1.37 | 1.42 | 1.47 | 1.53 | 1.59 | 1.66 | 1.72 | 1.79 | 1.86
2019 | 1.08 | 1.12 | 1.13 | 1.15 | 1.19 | 1.24 | 1.29 | 1.34 | 1.39 | 1.45 | 1.51 | 1.57
2020 | 1.02 | 1.06 | 1.07 | 1.09 | 1.12 | 1.17 | 1.21 | 1.26 | 1.31 | 1.37 | 1.42 | 1.48
2021 | 1.13 | 1.18 | 1.19 | 1.21 | 1.25 | 1.3 | 1.35 | 1.4 | 1.46 | 1.52 | 1.58 | 1.64
2022 | - | 1.04 | 1.05 | 1.07 | 1.1 | 1.15 | 1.19 | 1.24 | 1.29 | 1.34 | 1.4 | 1.45
2023 | - | - | 1.01 | 1.03 | 1.06 | 1.1 | 1.15 | 1.19 | 1.24 | 1.29 | 1.34 | 1.4
2024 | - | - | - | 1.02 | 1.05 | 1.09 | 1.14 | 1.18 | 1.23 | 1.28 | 1.33 | 1.38
2022-10-31
How to use this table: Each row allows an estimator to escalate a historical/current project to any future year. For instance, given a past project priced in the 2020 time frame, to approximate how much similar work would cost a decade later in 2030, just go down to the 2020 row and scan across to the 2030 column to get a multiplying factor of 1.31. The 2022 column is the only one based on actual CCIs; all the rest are forecasts.
Chimes Inflation Calculation
|  | Const Start Dt |  | Const End Dt
Est Base Yr |  | 2024-05-01 |  | 2024-10-01
2022 |  | 2024 |  | 2025
Inflation Rate each FY during Construction
1.05 | 2024 |  | Construction Year 1
1.07 | 2025 |  | Construction Year 2
Construction Year 3
Construction Year 4
Construction Year 5
Construction Year 6
Construction Year 7
2.12 | = Total
2 | = Count
1.06 | = CHIMES Inflation at mid-point of Construction
MnDOT’s established standard for calculating inflation is to take the average of the inflation from the EST BASE YEAR, then averaging the values between the stating state fiscal year selected and the ending state fiscal year selected, using the MnDOT RIC approved inflation tables. To see the current TPIC approved inflation factors, click on the question mark icon next to the INFLATED CON LETTING AMT to display the Inflation Conversion Factor table. If the person preparing the annual TPCE values believes they have information that would cause a deviation from MnDOT’s established standard, the inflated estimate value can be entered, however a detailed justification for using a value other than the CHIMES calculated INFLATED CON LETTING AMT must be entered in the NOTES area next to the Construction Let Amount $ESTIMATE.
Notes: | [10 empty] | [H]
Detail justification for using a value other than the chimes calculated inflated con letting amount must be entered in blue above
Note on A24: 11-1-20: This formula should include "2018". 11-1-21: This formula should include "2019". 11-1-22: This formula should include "2020". 11-1-23: This formula should include "2021". 11-1-24: This formula should include "2022". This same concept also applies to the next six cells in column "A".
Note on C30: This assumes a maximum of seven construction seasons on any MnDOT project.

## CHIMES Entry
This entire page, other then NOTES, is automatically populated from the TPCE worksheetThe CHIMES Total Project Cost Estimate is MnDOT’s authoritative source for maintaining and talking about TPCE. The notes if filled out by the cost estimator on the chimes inflation worksheet. The information shown in the project data TPCE section is the responsibility of the project manager before letting, and construction resident engineer after letting. The engineer responsible for the estimates may delegate entry of this information to another user, but is still responsible for the accuracy of the entered information.
CHIMES TPCE Entry Form |  |  |  | NAME: | This project will consist of a road realignment and replacement of roadside infrastructure within the project limits.
|  |  |  | ESTIMATE DATE: | 2023-07-31
|  |  |  | SP: | 3604-80
|  |  |  | TH: | 11
Total Project Cost Estimate
Est Base Year (State FY) | TPCE Stage | Const Start Dt | Const End Dt | Est Let Amount | Inflated Let Amount
2022 | 0 | 2024-05-01 | 2024-10-01 | 3002951 | 3183128.06
|  |  |  | Project Budget inflated and rounded,not including partner cost = | 4520000
Type of Cost
[A] Construction Let Amount |  | 3200000 | Same as "Inflated Let Amount"
[B] Post Letting Construction Costs |  | 180000 | CO / Overruns. Gut check about 4% of Construction Let Amount [A]
[C] Other Project Costs |  | 0 | MnDOT Costs that are not in the main construction contract.
[D] Preliminary Engineering |  | 400000 | Preletting / All costs related to design, etc. Gut check about 12% of Const. Let Amount [A]
[E] Construction Engineering |  | 600000 | Construction Inspection, etc. Gut check about 8% of Construction Let Amount [A]
[F] Right of Way |  | 140000 | ROW Cost + ROW Engineering Labor Costs. Engineering gut check is 12% of Right of Way Cost
[G] Partner Funding |  | 0
| Total = | 4520000 | TPCE does including partner funding
[H] NOTES: |  | 0 | only needs to be filled out if the person preparing the annual TPCE values believes they have information that would cause a deviation from MnDOT’s established standard, the inflated estimate value can be entered, however a detailed justification for using a value other than the CHIMES calculated INFLATED CON LETTING AMT must be entered in the NOTES area in Chimes next to the Construction Let Amount $ESTIMATE.
Note on C9: This cell will be filled out by the PM.
Note on C12: From CHIMES: Construction Let Amount: For Trunk Highway projects this is updated to show the amount of the annual estimates. Upon award of the construction contract, the last estimate is replaced with the construction contract award amount. For all other projects enter total amount of the agreement with the sub-recipient of federal funds, including any matching funds and non-participating funds.
Note on C13: From CHIMES: Post Letting Construction Cost: For Trunk Highway projects only. Includes any changes to the initial construction contract award amount. Post Letting Construction costs include supplemental agreements; cost overruns; escalation clauses; settlements; etc.
Note on C14: These are costs outside of the main construction contract. From CHIMES: Other Project Costs: For Trunk Highway projects only. Other Elements are for agreements that support the construction phase of the project and are for work not included in the construction contract. Examples include State furnished material, Municipal Agreements, Utility work and Traffic Control.
Note on C15: From CHIMES: Preliminary Engineering: The costs incurred to get the project ready for construction, through project award/award encumbrance date, including internal salaries; consultants; equipment used; materials; and allowable additives.
Note on C16: From CHIMES: Construction Engineering: All engineering and oversite costs incurred during the construction phase of a project, from the date of award/award encumbrance through final project closeout, including internal salary; consultants; equipment use; materials and allowable additives.
Note on C17: From CHIMES: Right of Way: All the costs associated project of Right of Way acquisition, including property settlement; internal salaries; consultants; equipment used; materials; and allowable additives.
Note on F13: Change orders, or overruns.

## Change Summary
Change Made By: | Date | Reasons for Cost Change between the Current Estimate and the Last Estimate:

## items under each pull down menu
TPCE Stage: | CONSTRUCTION_LET_AMOUNT | POST_LETTING_CON_COSTS | These are all Other_Project_Costs in Chimes |  |  | PRELIMINARY_ENGINEERING | CONSTRUCTION_ENGINEERING | internal or external | RIGHT_OF_WAY | types of ROW property
Chip Years | Project Letting Cost(SEQ pay items) | CO/Overruns | Preconstruction Cost | During Construction Cost | Post Construction Cost | Comm/Public Involvement | Administration | Internal | Standard Real Estate Purchase - Partial Take | Land- Ag
Scoping | Project Letting Cost(SEQ pay items)-env mitigation | Incentives/disincentives | Separate Contract- Environmental Mitigation | Separate Contract- Environmental Mitigation | Separate Contract- Environmental Mitigation | Contamination Investigation | Traffic Management | External | Standard Real Estate Purchase - Total Take | Land- Commercial
Enter into STIP-Baseline | Project Letting Cost(SEQ pay items)-env cleanup | Escalation clauses | Separate Contract- Environmental Clean-Up | Separate Contract- Environmental Clean-Up | Separate Contract- Environmental Clean-Up | Detailed Design |  |  | Tempary Easement | Land- Resident Building
Annual update | Project Letting Cost(SEQ pay items)-com/public involvement | Contractor settlements | Agreement- Major utility relocation costs | Construction Traffic Mgmt. - Extraordinary Reinforcement | Agreement- Detours and Haul Roads | Environmental Studies |  |  | Right to construct | Residential Property
Final Layout | Project Letting Costs bridge estimate (SEQ items) |  | Agreement- RR Costs | Construction Traffic Mgmt. - Incident Management | Separate Contract or Agreement- Landscape | Predesign/Scoping |  |  | Legal fees | Commercial property
60% plan | Construction timing ex- A plus B |  | State Furnished Materials | Other | Turnback | Traffic Management |  |  | Legal settlement
90% plan | Other item included in contract at time of award |  | Cooperative Agreement | Agreement- RR Costs | Intersection Lighting Power Source Costs | Other
100% plan |  |  | Separate Contract or Agreement- Landscape | Agreement- Major utility relocation costs | Agreement- RR Costs
Scope ammendment after 30% |  |  | Turnback |  | Agreement- Major utility relocation costs
Scope ammendment after 60% |  |  | Intersection Lighting Power Source Costs
Scope ammendment after 90% |  |  | Other
Scope ammendment after plan submittal
Construction substantially completed
Note on A6: Bridget Miller: normally need an estimate with layout to discuss splits and costs with locals.
Note on A10: Bridget Miller: any scoping ammendment should revisit if there is a cost change and if so update their budget
Note on A11: Bridget Miller: any scoping ammendment should revisit if there is a cost change and if so update their budget
Note on A12: Bridget Miller: any scoping ammendment should revisit if there is a cost change and if so update their budget
Note on C2: Bridget Miller: No longer have SA, paid for as CO
Note on C3: Bridget Miller: paid for as Change Orders now
Note on D1: Bridget Miller: These costs are only broken out as a way to help you track what has been spent and what is going to be spent after letting and closeout. Several items can be paid in any of the 3 rows. So you can just estimate when and how much if you don't know or leave it all in one group at the start.
Note on D5: Bridget Miller: Utility relocations are paid for as an agreement and are not paid as part of the construction let cost. They can be paid pre, during, or post, but most commonly paid pre.
Note on D6: Bridget Miller: Generally, for MnDOT TH projects that require a RR agreement, the Rail Office will reimburse the RR directly for all flagging and other charges that are contained within the RR agreement. We do not, as a practice, ask our contractors to reimburse the RR then have MnDOT reimburse the contractor.The costs to reimburse the RR are funded by the districts as part of the Project’s cost but not related to construction costs
Note on E8: Bridget Miller: Generally, for MnDOT TH projects that require a RR agreement, the Rail Office will reimburse the RR directly for all flagging and other charges that are contained within the RR agreement. We do not, as a practice, ask our contractors to reimburse the RR then have MnDOT reimburse the contractor.The costs to reimburse the RR are funded by the districts as part of the Project’s cost but not related to construction costs
Note on E9: Bridget Miller: Utility relocations are paid for as an agreement and are not paid as part of the construction let cost. They can be paid pre, during, or post, but most commonly paid pre.
Note on F9: Bridget Miller: Generally, for MnDOT TH projects that require a RR agreement, the Rail Office will reimburse the RR directly for all flagging and other charges that are contained within the RR agreement. We do not, as a practice, ask our contractors to reimburse the RR then have MnDOT reimburse the contractor.The costs to reimburse the RR are funded by the districts as part of the Project’s cost but not related to construction costs
Note on F10: Bridget Miller: Utility relocations are paid for as an agreement and are not paid as part of the construction let cost. They can be paid pre, during, or post, but most commonly paid pre.