## The Purpose and Need of a TPCE
The Purpose and Need of a TPCE
Purpose: A Total Project Cost Estimate is required for every project that is part of the state transportation improvement plan or program. Every project SP has an entry into CHIMES, and the results of each project TPCE is entered into CHIMES in the project section titled Total Project Cost Estimate for each project. This CHIMES Total Project Cost Estimate section is MnDOT’s authoritative source for accurate cost information for each project
Responsibility: Although completing the TPCE and CHIMES entry may be delegated, it is the responsibility of the project manager for the accuracy and entry of the estimated costs into CHIMES prior to project letting. After the letting has occurred, the accuracy and entries into CHIMES then becomes the responsibility of the resident engineer.
Shortly after a project has been let, actual costs will be available for viewing in CHIMES. Within the CHIMES Total Project Cost Estimate section, the line in the section labeled “$COMMITED” shows the actual costs from SWIFT expenditures.
Legislative Requirement: Need A Total Project Cost Estimate is needed to assist in complying with MN Statutes 174.56 Report on Major Highway Projects, Trunk Highway Fund Expenditures, and Efficiencies. This statute requires that the Commissioner of Transportation submit a report by December 15th of each year for projects with a total cost of at least $15 million for the metropolitan highway district and $5 million for the nonmetropolitan districts. Some of the required information specified by the statute pertaining to the TPCE include, a) Cost at the time of entry into the state transportation improvement plan b) Planning estimate c) Engineer’s estimate cost d) Award price e) Final cost 6 months after substantial completion f) Supplemental Agreements or cost overruns/cost savings For a more in-depth explanation of Minnesota Statute 174.56 and its requirements, click the link below.
174.56 Report on Major Highway Projects, Trunk Highway Fund Expenditures, and Efficiencies

## TPCE Template
TOTAL PROJECT COST ESTIMATE (TPCE) DESIGN-BID-BUILD | [12 empty] | fill in blue
Project Information | SP : | 8824-239 | Trunk Highway: | I 94 |  | Estimate's Completion Date: | 2023-07-30 |  | CONSTRUCTION START DATE |  | 2028-01-27 | FY 2028 | pull down selction in darker blue
| District : | 4 | Prime Element ID : |  | TPCE Stage: | Scoping | Fiscal Year of Letting: | 2024 | CONSTRUCTION END DATE |  | 2028-06-30 | FY 2028 | Last Updated 11/10/2022
| Project Length: | 29.57 MILES | Project Description: (Scope & Location) | DISTRICT WIDE SNOW FENCING (LIVING AND STRUCTURAL) VARIOUS LOCATIONS ALONG TH 94 |  |  |  |  | CHIMES INFLATION |  | 1.14
DIVISION | GROUP (I) | CATEGORY (II) | DETAILS (III) | BASE ESTIMATE (IV) | CONTINGENCY (V) OR Risk (Choose Largest) | TOTAL (VI) | FY OF LETTING (INFLATED) (VII) | FY of Letting (Inflated) split between local/Non MnDOT and MnDOT |  |  |  | INFLATED ROUNDED AMOUNT (VIII) |  | Rounding rules applied to construction costs:
[8 empty] | MNDOT FUNDS |  | LOCAL FUNDS |  |  |  | i. For projects under $1,000,000, round to the next $10,000. (i.e. – a $156,123.86 project would round to $160,000). ii. For projects $1,000,000 to $100,000,000, round to the next $100,000. (i.e. – a $1,509,000 project would round to $1,600,000 and a $12,772,000 project would round to $12,800,000). iii. For projects greater than $100 million, round to the next million. (i.e. – a $300,500,000 project would round to $301,000,000).
[8 empty] | % |  | %
Construction Contract | CONSTRUCTION_LET_AMOUNT | Project Letting Cost(SEQ pay items) |  | 9350149 | 954650.47 | 10304799.47 | 11747471.3958 | 100% | 11747471.3958 | 0% | 0
|  | Project Letting Cost(SEQ pay items) | RISK: DOUBLE ROW SHRUB LIVING FENCE |  | 573940 | 573940 | 654291.6 | 100% | 654291.6 | 0% | 0
|  | Project Letting Cost(SEQ pay items) | RISK: GRUBBING |  | 1849 | 1849 | 2107.86 | 100% | 2107.86 | 0% | 0
|  | Project Letting Cost(SEQ pay items) | RISK: REMOVE BARBED WIRE FENCE |  | 73499 | 73499 | 83788.86 | 100% | 83788.86 | 0% | 0
|  | Project Letting Cost(SEQ pay items) | RISK: WOOD BRACE ASSEMBLY |  | 10920 | 10920 | 12448.8 | 100% | 12448.8 | 0% | 0
|  | Project Letting Cost(SEQ pay items) | RISK: WOVEN WIRE FENCE |  | 357950 | 357950 | 408063 | 100% | 408063 | 0% | 0
| 1. Project Cost Estimate at time of letting, Construction Contract Items Only ( Today's Dollars ) |  |  | 9350149 | 1972808.47 | 11322957.47 | 12908171.5158 | 12908171.5158 |  | 0 |  | 13000000 | [A] | The red lettering designates the totals listed by the same lettering in the CHIMES TPCE Entry Form.
| POST_LETTING_CON_COSTS | CO/Overruns | 7% CONSTRUCTION COST | 674146 |  | 674146 | 768526.44 | 100% | 768526.44 | 0% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
| 2. Project Cost Estimate after letting, Construction Contract Items Only ( Today's Dollars ) |  |  | 674146 | 0 | 674146 | 768526.44 | 768526.44 |  | 0 |  | 770000 | [B]
Total Construction Contract Amount |  |  |  | 10024295 | 1972808.47 | 11997103.47 | 13676697.9558 | 0 |  | 0 |  | 13770000
Other Project Costs | OTHER_PROJECT_COSTS |  |  |  |  | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
| Preconstruction Cost (C) |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| OTHER_PROJECT_COSTS |  |  |  |  | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
| During Construction Cost (D) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OTHER_PROJECT_COSTS |  |  |  |  | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
| Post Construction Cost (E) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3. Other Project Costs (C+D+E) (Not in Main contract, Not engineering or ROW) |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [C]
Total Construction Costs |  |  |  | 10024295 | 1972808.47 | 11997103.47 | 13676697.9558 | 13676697.9558 |  | 0 |  | 13770000
DIVISION | GROUP (I) | CATEGORY (II) | DETAILS (III) | BASE ESTIMATE (IV) | CONTINGENCY (V) OR Risk (Choose Largest) | TOTAL (VI) | FY OF LETTING (INFLATED) (VII) | FY of Letting (Inflated) split between local/Non MnDOT and MnDOT |  |  |  | INFLATED ROUNDED AMOUNT (VIII) |  | Rounding rules applied to Engineering costs:
[8 empty] | MNDOT FUNDS |  | LOCAL FUNDS |  |  |  | i. For projects under $300,000, round up to the next $10,000 ii. For projects over $300,000, round up to the next $100,000.
[8 empty] | % |  | %
Engineering | PRELIMINARY_ENGINEERING |  | internal or external
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
|  | Other | Internal | 750000 |  | 750000 | 855000 | 100% | 855000 | 0% | 0
| 4.Preliminary Engineering Total |  |  | 750000 | 0 | 750000 | 855000 | 855000 |  | 0 |  | 900000 | [D] | last resort use rule of thumb if you don't have a TTAA or a good estimate is 12% of construction costs
| CONSTRUCTION_ENGINEERING |  | internal or external
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
[6 empty] | 0 | 0 |  | 0 | 100% | 0
|  | Administration | Internal | 450000 |  | 450000 | 513000 | 100% | 513000 | 0% | 0
| 5.Construction Engineering Total |  |  | 450000 | 0 | 450000 | 513000 | 513000 |  | 0 |  | 600000 | [E] | last resort use rule of thumb if you don't have a better estimate is 8% of construction costs
Total Engineering Costs |  |  |  | 1200000 | 0 | 1200000 | 1368000 | 1368000 |  | 0 |  | 1500000
Right of Way | GROUP (I) | CATEGORY (II) | DETAILS (III) | BASE ESTIMATE (IV) | CONTINGENCY (V) OR Risk (Choose Largest) | TOTAL (VI) | FY OF LETTING Do not apply inflation due to the fact that the R/W estimate already applied market conditions in its calculation. (VII) | FY of Letting split between local/Non MnDOT and MnDOT |  |  |  | INFLATED ROUNDED AMOUNT (VIII) |  | No rounding rules have been applied to ROW costs:
[8 empty] | MNDOT FUNDS |  | LOCAL FUNDS |  |  |  | For costs, communicate with the District R/W engineer/manager for the cost estimates and whether or not they have rounded the R/W cost provided. If Right of Way rounding is not transferred from the R/W cost sheet, the rounding will need be consistent with the OLM rounding rules in the R/W cost estimate tool.
[8 empty] | % |  | %
|  | Standard Real Estate Purchase - Partial Take | Land- Ag | 1612763.71 |  | 1612763.71 | 1612763.71 | 100% | 1612763.71 | 0% | 0
[6 empty] | 0 |  |  | 0 | 100% | 0
[6 empty] | 0 |  |  | 0 | 100% | 0
[6 empty] | 0 |  |  | 0 | 100% | 0
[6 empty] | 0 |  |  | 0 | 100% | 0
[6 empty] | 0 |  |  | 0 | 100% | 0
|  | ROW LABOR | INTERNAL | 193531.68 |  | 193531.68 | 220626.1152 | 100% | 220626.1152 | 0% | 0 |  |  | last resort if you don't have a better estimate and contract, ROW engineering rule of thumb is 12% of ROW costs
| 6. Total Right of Way Costs (including labor/engineering) |  |  | 1806295.39 | 0 | 1806295.39 | 1833389.8252 | 1833389.8252 |  | 0 |  | 1900000 | [F]
Total ROW Costs ( INCLUDING ROW LABOR COSTS ) |  |  |  | 1806295.39 | 0 | 1806295.39 | 1833389.8252 | 1833389.8252 |  | 0 |  | 1900000
DIVISION | GROUP (I) | CATEGORY (II) | DETAILS (III) | BASE ESTIMATE (IV) | CONTINGENCY (V) OR Risk (Choose Largest) | TOTAL (VI) | FY OF LETTING (INFLATED) (VII)
Partner Funding | PARTNER_FUNDING |  |  |  |  | 0 | 0
Total Partner Funding ( These costs are not included elsewhere on this sheet, it is only for funds that do not go through chimes. Very few projects will have anything entered here. ) |  |  |  | 0 | 0 | 0 | 0 | [G]
PROJECT TOTAL |  |  |  | Total Base Cost | Total Contingency | Toal cost | Total inflated Cost | Total inflated cost rounded cost
TPCE, this includes Partner funding |  |  |  | 13030590.39 | 1972808.47 | 15003398.86 | 16878087.781 | 17170000
Total Budget, this goes through chimes and does not include Partner funding |  |  |  | 13030590.39 | 1972808.47 | 15003398.86 | 16878087.781 | 17170000
Estimator: | CHRISTIAN TUNHEIM |  |  | Approval By:
Project Manager: |  | JEREMY PETERSON |  | Print Name:
Title:
Date:
Note on M3: Bridget Miller: Month/Date/Year
Note on M4: Bridget Miller: Month/Date/Year
Note on G8: Amount based on Expected Value (Risk Assessment) [PxI]
Note on C11: Bridget Miller: For TH projects, this is updated to show the amounts of the annual estimate. Upon award of the construction contract, the latest estimate is replaced with the construction contract award amount.
Note on H18: If the letting was today, this would be the cost.
Note on I18: This is the estimated bid amount for the future scheduled letting date. This number includes inflation.
Note on C20: Bridget Miller: For TH projects only. Includes any changes to the initial construction contract award amount.
Note on H25: If the letting was today, this would be the cost.
Note on I25: This is the estimated bid amount for the future scheduled letting date. This number includes inflation.
Note on B28: Bridget Miller: For TH projects only. Other Elements are for agreements that support the construction phase of the project and are for work not included in the onstruction contract. See pull down menu tab for examples
Note on G64: Amount based on Expected Value (Risk Assessment) [PxI]
Note on C67: Bridget Miller: Cost incurred to get project ready for construction, through project award/award encumbrance date, including salaries, consultants, equipment used, and materials to do the engineering.
Note on N82: Bridget Miller Rule of thumb is 12% construction cost
Note on C84: Bridget Miller: All engineering and oversite costs incurred during the construction phase of a project, from the date of award/award encumbrance through final project closeout, including internal salary, consultant equipment used in the field, and materials needed to do engineering.
Note on N89: Bridget Miller: Rule of thumb is 8%
Note on G93: Amount based on Expected Value (Risk Assessment) [PxI]
Note on L103: Bridget Miller: If using ROW from your ROW engineer estimating tool, put the rounded cost information here to overwrite calculations. ROW is rounded differently
Note on N103: Bridget Miller: Need to fill in, see yellow note above
Note on G107: Amount based on Expected Value (Risk Assessment) [PxI]

## CHIMES Inflation Calculation
Cost Estimate Inflation Conversion Factor Table
Historical/Current Baseline Fiscal Year ↓ | Future Projection Fiscal Year
| 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033
YOY D% | 13% | 4% | 1% | 2% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4%
2017 | 1.48 | 1.53 | 1.55 | 1.58 | 1.63 | 1.69 | 1.76 | 1.83 | 1.9 | 1.98 | 2.06 | 2.14
2018 | 1.28 | 1.33 | 1.35 | 1.37 | 1.42 | 1.47 | 1.53 | 1.59 | 1.66 | 1.72 | 1.79 | 1.86
2019 | 1.08 | 1.12 | 1.13 | 1.15 | 1.19 | 1.24 | 1.29 | 1.34 | 1.39 | 1.45 | 1.51 | 1.57
2020 | 1.02 | 1.06 | 1.07 | 1.09 | 1.12 | 1.17 | 1.21 | 1.26 | 1.31 | 1.37 | 1.42 | 1.48
2021 | 1.13 | 1.18 | 1.19 | 1.21 | 1.25 | 1.3 | 1.35 | 1.4 | 1.46 | 1.52 | 1.58 | 1.64
2022 | - | 1.04 | 1.05 | 1.07 | 1.1 | 1.15 | 1.19 | 1.24 | 1.29 | 1.34 | 1.4 | 1.45
2023 | - | - | 1.01 | 1.03 | 1.06 | 1.1 | 1.15 | 1.19 | 1.24 | 1.29 | 1.34 | 1.4
2024 | - | - | - | 1.02 | 1.05 | 1.09 | 1.14 | 1.18 | 1.23 | 1.28 | 1.33 | 1.38
[11 empty] | Latest Inflation Data Updated | 2022-10-31
How To Use This Table: Each row allows an estimator to escalate a historical/current project to any future year. For instance, given a past project priced in the 2020 time frame, to approximate how much similar work would cost a decade later in 2030, just go down to the 2020 row and scan across to the 2030 column to get a multiplying factor of 1.31. The 2022 column is the only one based on actual Construction Cost Indexes (CCI); all the rest are forecasts.
Chimes Inflation Calculation | [8 empty] | Fields in Red below are automatically populated when the construction start and end dates are entered into the TPCE Template Project Information section.
|  | Const Start Date |  | Const End Date
Estimate Base Year |  | 2028-01-27 |  | 2028-06-30
2024 |  | 2028 |  | 2028 |  |  |  |  | The Estimate Base Year must be entered. Construction Date fields are automatically populated as designated in the note above.
Inflation Rate each FY during Construction
1.14 | 2028 |  | Construction Year 1
Construction Year 2
Construction Year 3
Construction Year 4
Construction Year 5
Construction Year 6
Construction Year 7
1.14 | = Total
1 | = Count
1.14 | = CHIMES Inflation at Mid-Point of Construction
MnDOT’s established standard for calculating inflation is to take the average of the inflation from the EST BASE YEAR, then averaging the values between the starting state fiscal year and the ending state fiscal year, using the MnDOT Resource Investment Committee (RIC) approved inflation tables. Within CHIMES, to view the current TPIC approved inflation factors, click on the question mark icon next to the INFLATED CON LETTING AMT to display the Inflation Conversion Factor table. If the person preparing the annual TPCE costs believes they have information that would cause a deviation from MnDOT’s established standard, the inflated estimate value can be entered, however a detailed justification (entered below) for using a value other than the CHIMES calculated INFLATED CON LETTING AMT must also be entered in the NOTES area next to the Construction Let Amount $ESTIMATE.
Notes: | [10 empty] | [H] | (Enter Notes in first cell)
Detail justification for using a value other than the chimes calculated inflated con letting amount must be entered in blue area above.
Notes entered above are automatically transferred to the CHIMES TPCE Entry Form tab.
Note on A1: Bridget Miller: MnDOT’s established standard for calculating inflation is to take the average of the inflation from the EST BASE YEAR, then averaging the values between the stating state fiscal year selected and the ending state fiscal year selected, using the MnDOT RIC approved inflation tables. To see the current TPIC approved inflation factors, click on the question mark icon next to the INFLATED CON LETTING AMT to display the Inflation Conversion Factor table.
Note on A25: The Estimated Base Fiscal Year entered into cell A20 will determine which row of the table above the inflation rates will be taken from. The fiscal years (B24:B30) from the Construction Start and End Dates, and associated inflation rates (A24:A30) for the Estimate Base Fiscal Year entered into cell A20, will be used to calculate the Mid-Point of Construction Inflation Rate. These are all automatically populated and calculated.
Note on C31: This assumes a maximum of seven construction seasons on any MnDOT project.

## CHIMES TPCE Entry Form
This CHIMES TPCE Entry Form is a listing and summation of TPCE costs that are entered into CHIMES by the categories listed below. All costs below, other then the NOTES section at the bottom, are automatically populated from the TPCE worksheet. The NOTES section is automatically populated from the CHIMES Inflation tab note section. Within CHIMES, the Total Project Cost Estimate section is MnDOT’s authoritative source on project costs. As with the TPCE, the CHIMES TPCE Entry Form is the responsibility of the project manager and/or the construction resident engineer.
CHIMES TPCE Entry Form |  |  |  | NAME: | DISTRICT WIDE SNOW FENCING (LIVING AND STRUCTURAL) VARIOUS LOCATIONS ALONG TH 94
|  |  |  | DATE OF ESTIMATE: | 2023-07-30
|  |  |  | SP: | 8824-239
|  |  |  | TH: | I 94
Total Project Cost Estimate
Est Base Year (State FY) | TPCE Stage | Construction Start Date | Construction End Date | Estimate Let Amount | Inflated Let Amount
2024 | Scoping | 2028-01-27 | 2028-06-30 | 11322957.47 | 12908171.5158
|  |  |  | Project Budget inflated and rounded,not including partner cost = | 17170000
Type of Cost
[A] Construction Let Amount |  | 13000000 | Same as "Inflated Let Amount"
[B] Post Letting Construction Costs |  | 770000 | CO / Overruns. Gut check about 4% of Construction Let Amount [A]
[C] Other Project Costs |  | 0 | MnDOT Costs that are not in the main construction contract.
[D] Preliminary Engineering |  | 900000 | Preletting / All costs related to design, etc. Gut check about 12% of Construction Let Amount [A]
[E] Construction Engineering |  | 600000 | Construction Inspection, etc. Gut check about 8% of Construction Let Amount [A]
[F] Right of Way |  | 1900000 | ROW Cost + ROW Engineering Labor Costs. Engineering gut check is 12% of Right of Way Cost
[G] Partner Funding |  | 0
| Total = | 17170000 | Includes Partner Funding
[H] NOTES: |  | 0 | These NOTES only need to be documented if the person completing the annual TPCE believes they have information that would cause a deviation from MnDOT’s established standard, the inflated estimate value can be entered, however a detailed justification for using a value other than the CHIMES calculated INFLATED CON LETTING AMT must be entered in the NOTES area in Chimes next to the Construction Let Amount $ESTIMATE.
Note on C12: From CHIMES: Construction Let Amount: For Trunk Highway projects this is updated to show the amount of the annual estimates. Upon award of the construction contract, the last estimate is replaced with the construction contract award amount. For all other projects enter total amount of the agreement with the sub-recipient of federal funds, including any matching funds and non-participating funds.
Note on C13: From CHIMES: Post Letting Construction Cost: For Trunk Highway projects only. Includes any changes to the initial construction contract award amount. Post Letting Construction costs include supplemental agreements; cost overruns; escalation clauses; settlements; etc.
Note on F13: Change orders, or overruns.
Note on C14: These are costs outside of the main construction contract. From CHIMES: Other Project Costs: For Trunk Highway projects only. Other Elements are for agreements that support the construction phase of the project and are for work not included in the construction contract. Examples include State furnished material, Municipal Agreements, Utility work and Traffic Control.
Note on C15: From CHIMES: Preliminary Engineering: The costs incurred to get the project ready for construction, through project award/award encumbrance date, including internal salaries; consultants; equipment used; materials; and allowable additives.
Note on C16: From CHIMES: Construction Engineering: All engineering and oversite costs incurred during the construction phase of a project, from the date of award/award encumbrance through final project closeout, including internal salary; consultants; equipment use; materials and allowable additives.
Note on C17: From CHIMES: Right of Way: All the costs associated project of Right of Way acquisition, including property settlement; internal salaries; consultants; equipment used; materials; and allowable additives.

## Lists for Dropdown Menus
TPCE Stage: | CONSTRUCTION_LET_AMOUNT | POST_LETTING_CON_COSTS | These are all Other_Project_Costs in Chimes |  |  | PRELIMINARY_ENGINEERING | CONSTRUCTION_ENGINEERING | internal or external | RIGHT_OF_WAY | types of ROW property
Chip Years | Project Letting Cost(SEQ pay items) | CO/Overruns | Preconstruction Cost | During Construction Cost | Post Construction Cost | Comm/Public Involvement | Administration | Internal | Standard Real Estate Purchase - Partial Take | Land- Ag
Scoping | Project Letting Cost(SEQ pay items)-env mitigation | Incentives/disincentives | Separate Contract- Environmental Mitigation | Separate Contract- Environmental Mitigation | Separate Contract- Environmental Mitigation | Contamination Investigation | Traffic Management | External | Standard Real Estate Purchase - Total Take | Land- Commercial
Enter into STIP-Baseline | Project Letting Cost(SEQ pay items)-env cleanup | Escalation clauses | Separate Contract- Environmental Clean-Up | Separate Contract- Environmental Clean-Up | Separate Contract- Environmental Clean-Up | Detailed Design |  |  | Temporary Easement | Land- Resident Building
Annual update | Project Letting Cost(SEQ pay items)-com/public involvement | Contractor settlements | Agreement- Major utility relocation costs | Construction Traffic Mgmt. - Extraordinary Reinforcement | Agreement- Detours and Haul Roads | Environmental Studies |  |  | Right to construct | Residential Property
Final Layout | Project Letting Costs bridge estimate (SEQ items) |  | Agreement- RR Costs | Construction Traffic Mgmt. - Incident Management | Separate Contract or Agreement- Landscape | Predesign/Scoping |  |  | Legal fees | Commercial property
60% plan | Construction timing ex- A plus B |  | State Furnished Materials | Other | Turnback | Traffic Management |  |  | Legal settlement
90% plan | Other item included in contract at time of award |  | Cooperative Agreement | Agreement- RR Costs | Intersection Lighting Power Source Costs | Other
100% plan |  |  | Separate Contract or Agreement- Landscape | Agreement- Major utility relocation costs | Agreement- RR Costs
Scope amendment after 30% |  |  | Turnback |  | Agreement- Major utility relocation costs
Scope amendment after 60% |  |  | Intersection Lighting Power Source Costs
Scope amendment after 90% |  |  | Other
Scope amendment after plan submittal
Construction substantially completed
Note on D1: Bridget Miller: These costs are only broken out as a way to help you track what has been spent and what is going to be spent after letting and closeout. Several items can be paid in any of the 3 rows. So you can just estimate when and how much if you don't know or leave it all in one group at the start.
Note on C2: Bridget Miller: No longer have SA, paid for as CO
Note on C3: Bridget Miller: paid for as Change Orders now
Note on D5: Bridget Miller: Utility relocations are paid for as an agreement and are not paid as part of the construction let cost. They can be paid pre, during, or post, but most commonly paid pre.
Note on A6: Bridget Miller: normally need an estimate with layout to discuss splits and costs with locals.
Note on D6: Bridget Miller: Generally, for MnDOT TH projects that require a RR agreement, the Rail Office will reimburse the RR directly for all flagging and other charges that are contained within the RR agreement. We do not, as a practice, ask our contractors to reimburse the RR then have MnDOT reimburse the contractor.The costs to reimburse the RR are funded by the districts as part of the Project’s cost but not related to construction costs
Note on E8: Bridget Miller: Generally, for MnDOT TH projects that require a RR agreement, the Rail Office will reimburse the RR directly for all flagging and other charges that are contained within the RR agreement. We do not, as a practice, ask our contractors to reimburse the RR then have MnDOT reimburse the contractor.The costs to reimburse the RR are funded by the districts as part of the Project’s cost but not related to construction costs
Note on E9: Bridget Miller: Utility relocations are paid for as an agreement and are not paid as part of the construction let cost. They can be paid pre, during, or post, but most commonly paid pre.
Note on F9: Bridget Miller: Generally, for MnDOT TH projects that require a RR agreement, the Rail Office will reimburse the RR directly for all flagging and other charges that are contained within the RR agreement. We do not, as a practice, ask our contractors to reimburse the RR then have MnDOT reimburse the contractor.The costs to reimburse the RR are funded by the districts as part of the Project’s cost but not related to construction costs
Note on A10: Bridget Miller: any scoping ammendment should revisit if there is a cost change and if so update their budget
Note on F10: Bridget Miller: Utility relocations are paid for as an agreement and are not paid as part of the construction let cost. They can be paid pre, during, or post, but most commonly paid pre.
Note on A11: Bridget Miller: any scoping ammendment should revisit if there is a cost change and if so update their budget
Note on A12: Bridget Miller: any scoping ammendment should revisit if there is a cost change and if so update their budget