## Sample Tribal TIP
Name of |  | Red Lake Band of Chippewa Indians | [7 empty] | FY 2024 Annual |  | 2448622
Tribe | [9 empty] | Transportation Allocation
Tribal Transportation Improvement Plan
Priority | BIA Route # | Section | Project Length | Year of Constr |  | All Planning, Prelim Eng., Arch, Env, ROW Activities will be included as TOTAL PE costs per Project |  | Construction |  | Construction Engineering |  | Other | Total
Road Name
Location (Start and End Points)
[5 empty] | Description of Work | Estimated Cost | Who/How Work Done | Estimated Cost | Who/How Work Done | Estimated Cost | Who/How Work Done | Estimated Cost | Estimated Cost
1 | 170 | 10 | 0.2 | 2023 | Red Lake Streets East (West Street) | 9000 | Tribe | 60000 | Tribe | 30000 | Tribe |  | 99000
N47°52'34"; W95°00'14"; to N47°52'40"; W94°59'19"
Bituminous Resurfacing
1 | 171 | 10 | 0.3 | 2023 | Red Lake Streets East (North Street) | 13500 | Tribe | 90000 | Tribe | 45000 | Tribe |  | 148500
N47°52'40"; W94°59'19" to N47°52"42"; W94°59'30"
Bituminous Resurfacing
1 | 172 | 10 | 0.2 | 2023 | Red Lake Streets East (South Street) | 9000 | Tribe | 60000 | Tribe | 30000 | Tribe |  | 99000
N47°52'39"; W95°00'50" to N47°52'67"; W94°59'18"
Bituminous Resurfacing
1 | 173 | 10 | 0.2 | 2023 | Red Lake Streets East (Norway Dr.) | 9000 | Tribe | 60000 | Tribe | 30000 | Tribe |  | 99000
N47°52'34"; W94°50"52" to N47°52'40"; W94°59'19"
Bituminous Resurfacing
4 | 136 | 10 | 0.6 | 2023 | 1st. Avenue South (Thunder Lake Dr.) (BOT) | 7500 | Tribe | 180000 | Tribe | 90000 | Tribe |  | 277500
N47°52'21"; W91°01'17" to N47°52'32"; W95°01'28"
Bituminous Resurfacing
4 | 137 | 10 | 1.1 | 2023 | 3rd. Street East (BOT) | 7500 | Tribe | 25000 | Tribe | 10000 | Tribe |  | 42500
N47°52'26"; W95°01'21" to N47°52"08"; W95°01'31"
Bituminous Resurfacing
5 | 138 | 10 | 0.4 | 2023 | 3rd Street South (BOT) | 7500 | Tribe | 1000 | Tribe | 10000 | Tribe |  | 18500
N47°N47°52'32"; W95°01'09"
Bituminous Resurfacing
5 | 139 | 10 | 0.5 | 2023 | 2nd. Sve south (Crossroads) (BOT) | 7500 | Tribe | 40000 | Tribe | 10000 | Tribe |  | 57500
N47°52'08"; W95°01'36" to N47°52'08"; W95°01'09"
Bituminous Resurfacing
2 | 174 | 10-30 | 2.91 | 2023 | Thunder Lake Road (Phase III) | 190000 | Tribe | 1000 | Tribe | 1000 | Tribe |  | 192000
N47°51'53"; W94°57'43" to N47°51'08"; W94°50'54"
Project from end of Phase II to I.S. No. 40 & 18.
Grade, drain, gravel base and bituminous surfacing
8 | 50 | 1 | 0.5 | 2023 | Highway 1 Non-Motorized Trail (PH1) | 1000 | Tribe | 1000 | Tribe | 1000 | Tribe |  | 3000
Begin: Main Avenue Red Lake Agency; End: New gov't Center
Construct New Bituminous Surfaced Trail
7 | 50 | 2 | 1.1 | 2023 | Elementary School Non-Motorized Trail | 1000 | Tribe | 1000 | Tribe | 1000 | Tribe |  | 3000
Begin: 0+00 on Thunder Lake Dr.; End: Red Lake Elem Sch.
Construct New Bituminous Surfaced Trail
2 | 40 | 10 | 3 | 2023 | Nebish Redby Road | 75000 | Tribe | 891725 | Tribe | 75000 | Tribe |  | 1041725
N47°51'03", W94°50'46" to N47°52'21", W94°52'57"
Bituminous Resurfacing
12 | 18 | 90 | 3.6 | 2024 | Ponemah Road | 94500 | Tribe | 1000 | Tribe | 1000 | Tribe |  | 96500
N48°00'07", W94°48'48" to N48°01'40", W94°54'53"
Bituminous Resurfacing
14 | 332 | 10-150 | 55.7 | 2023 | Minnesota State Hwy. No. 1 Coop | 1000 | Tribe | 1000 | Tribe | 1000 | Tribe |  | 3000
West Reservation Boundary to East Reservation Boundary
Reconstruct Road
3 | 225 | 10 | 0.3 | 2023 | Mendota Ave. Redby | 7500 | Tribe | 36795 | Tribe | 1000 | Tribe |  | 45295
N47°52'38"; W94°55'11' to 47°52'46"; W94°55'14"
Bituminous Resurfacing
3 | 226 | 10 | 0.3 | 2024 | McBrides Road | 10000 | Tribe | 93801 | Tribe | 7500 | Tribe |  | 111301
N47°52'89"; W94°53'70' to 47°52'56"; W94°53'66"
Bituminous Resurfacing
3 | 227 | 10 | 0.7 | 2024 | McBrides Spur | 10000 | Tribe | 93801 | Tribe | 7500 | Tribe |  | 111301
N47°52'66"; W94°53'90' to 47°52'54"; W94°52'79"
Bituminous Resurfacing
[6 empty] | 460500 |  | 1449520 |  | 351000 |  |  | 2448622
[10 empty] | FY24 Total |  |  | 2448622 | 0.1
[10 empty] | Annual FY 2025 |  | 2693484.2
Transportation Allocation
Priority | BIA Route # | Section | Project Length | Year of Constr |  | All Planning, Prelim Eng., Arch, Env, ROW Activities will be included as TOTAL PE costs per Project |  | Construction |  | Construction Engineering |  | Other | Total
Road Name
Location (Start and End Points)
[5 empty] | Description of Work | Estimated Cost | Who/How Work Done | Estimated Cost | Who/How Work Done | Estimated Cost | Who/How Work Done | Estimated Cost | Estimated Cost
6 | 174 | 10-30 | 2.91 | 2024 | Thunder Lake Road (Phase III) | 150000 | Tribe | 2350759 | Tribe | 75000 | Tribe |  | 2575759
N47°51'53"; W94°57'43" to N47°51'08"; W94°50'54"
Project from end of Phase II to I.S. 40 & 18.
Grade, drain, gravel base and bituminous surfacing
7 | 50 | 1 | 4 | 2024 | Highway 1 Non-Motorized Trail (PH1) | 2000 | Tribe | 1000 | Tribe | 1000 | Tribe |  | 4000
Begin: New gov't Center to Redby
Construct New Bituminous Surfaced Trail
8 | 50 | 2 | 1.1 | 2024 | Elementary School Non-Motorized Trail | 1000 |  | 1000 | Tribe | 1000 | Tribe |  | 3000
Begin: 0+00 on Thunder Lake Dr.; End: Red Lake Elem Sch.
Construct New Bituminous Surfaced Trail
9 | 332 | 10-150 | 0.75 | 2024 | Minnesota State Hwy. No. 1 Coop | 1000 | Tribe | 1000 | Tribe | 1000 | Tribe |  | 2000
Safety upgrade town of Redby
Reconstruct Road
10 | 3 | 10 | 10 | 2024 | Clearwater road | 7500 | Tribe | 91225 | Tribe | 10000 | Tribe |  | 108725
N47°49'58"; W95°25'37' to 47°52'51"; W95°14'32"
Bituminous Resurfacing
[10 empty] | FY25 Total |  |  | 2693484 | 0.1
[10 empty] | Annual FY 2026 |  | 2962832.4
Transportation Allocation
Priority | BIA Route # | Section | Project Length | Year of Constr |  | All Planning, Prelim Eng., Arch, Env, ROW Activities will be included as TOTAL PE costs per Project |  | Construction |  | Construction Engineering |  | Other | Total
Road Name
Location (Start and End Points)
[5 empty] | Description of Work | Estimated Cost | Who/How Work Done | Estimated Cost | Who/How Work Done | Estimated Cost | Who/How Work Done | Estimated Cost | Estimated Cost
6 | 174 | 20-30 | 2.9 | 2025 | Thunder Lake Road (Phase III) | 5000 | Tribe | 2224102 | Tribe | 36000 | Tribe |  | 2265102
N47°51'53"; W94°57'43" to N47°51'08"; W94°50'54"
project from end of Phase II to I.S. 40 &18.
Grade, drain, gravel base and bituminous surfacing
12 | 28 | 10 | 5 | 2025 | Northeast Boundary Road | 38300 | Tribe | 315082 | Tribe | 25000 | Tribe |  | 378382
Begin on I.S. 18; End on I.S. 25
Bituminous Surfacing
11 | 25 | 1-2 | 10.5 | 2025 | North Shore Road | 75000 | Tribe | 229348 | Tribe | 15000 | Tribe |  | 319348
Begin on I.S, 18; end at East Res. Boundary
Bituminous Overlay
Grade, Drain, Bravel Base and Bituminoous Surfacing
[10 empty] | FY26 Total |  |  | 2962832 | 0.1
[10 empty] | Annual FY 2027 |  | 3259115.2
Transportation Allocation
Priority | BIA Route # | Section | Project Length | Year of Constr |  | All Planning, Prelim Eng., Arch, Env, ROW Activities will be included as TOTAL PE costs per Project |  | Construction |  | Construction Engineering |  | Other | Total
Road Name
Location (Start and End Points)
[5 empty] | Description of Work | Estimated Cost | Who/How Work Done | Estimated Cost | Who/How Work Done | Estimated Cost | Who/How Work Done | Estimated Cost | Estimated Cost
6 | 174 | 10-30 | 2.75 | 2026 | Thunder Lake Road (Phase III) | 315000 | Tribe | 2211833 | Tribe | 5000 | Tribe |  | 2531833
N47°51'53"; W94°57'43" to N47°51'08"; W94°50'54"
project from end of Phase II to I.S. No. 40 & 18.
Grade, drain, gravel base and bituminous surfacing
12 | 28 | 10 | 5 | 2026 | Northeast Boundary Road | 150000 | Tribe | 69450 | Tribe | 6000 | Tribe |  | 225450
Begin on I.S. 18; End on I.S. 25
Bituminous Surfacing
11 | 25 | 10 | 10.5 | 2026 | North Shore Road | 395000 | Tribe | 1000 | Tribe | 5000 | Tribe |  | 401000
Begin on I.S, 18; end at East Res. Boundary
Bituminous Overlay
16 | 502 | 10 | 2.5 | 2026 | Thunder Lake/ Highway 1 Connector | 94832 | Tribe | 1000 | Tribe | 5000 | Tribe |  | 100832
Begin Thunder Lake Road; End MN Hwy. One
Grade, Drain, Gravel Base and Bituminous Surfacing
[10 empty] | FY27 Total |  |  | 3259115
Project Information: | [5 empty] | Who/How Work Done: Possible Choices
BIA Route # |  | List all routes that will be worked on. |  |  |  | BIA | BIA will perform direct service (DS) work for the Tribe as outlined in a Retained Service Agreement (RSA)
as approved/signed by the Tribe and BIA.
Section |  | List only those sections that will be worked on along with corresponding length |  |  |  |  | (Self Determination, G2G, and Self Gov Tribes can all elect to receive these services)
Location |  | List start and end points of where work will be performed (road names, rivers, end, etc.) |  |  |  | 638 | Self Determination Tribe will enter into a P638 contract with the BIA and either perform work with
in-house staff or subcontract work out to consultant/contractor.
Description |  | List as much detail as you can including existing road type and work to be performed
of Work | [5 empty] | Coop | Tribe can receive funding through a P638 contract, G2G, or Self Gov Agreement. Tribe will then
enter into a 2-party (Coop) agreement with County, State, Township etc. who will usually serve as
the lead agency for the project.
Estimated Cost: |  |  | Provide dollar amounts that you estimate will be required for each project/phase
|  |  | utilizing new funds from that year only. Prior year money obligated to contract |  |  | Tribe | Tribe administers program/project through a Self Governance or G2G Agreement.
should not be listed here.