## Plan
Reconditioning & Rehabilitation |  |  | Paser Rating 1-10
|  |  | 1= Poor | 10 = Excellent
Road | From | To | Paser Rating | Scheduled Year | Budget Cost Construction | Mileage | Notes | Grant | County Cost | Others Cost | Other Info
CTH TA | CTH T | CTH A | 2 | 2021 | 1354657 | 2.69 | Rural Section |  | 1354657
Concrete Driveways |  |  |  | 2021 | 50000 |  | Construction |  | 50000
CTH YY | STH 14 | STH 33 | 3 | 2021 | 1492298 | 3.59 | Rural Section & Safety Project | 272595 | 1219703 |  | CHIP
CTH M | CTH B | Wolter Road | 3 | 2022 | 2584851 |  | Rural Section |  | 2584851
CTH M | CTH O | Wolter Road | 3 | 2022 | 2657362 |  | Rural Section | 2125890 | 531472 |  | STP Rural
Concrete Driveways |  |  |  | 2022 | 50000 |  | Construction |  | 50000
CTH TT | CTH V | CTH T | 2 | 2022 | 788955 | 1.76 | Rural Section |  | 788955
CTH T Safety Improvements | CTH C | STH 53 | 6 & 7 | 2023 | 1100000 |  | Safety Improvements |  | 1100000
Concrete Driveways |  |  |  | 2023 | 50000 |  | Construction |  | 50000
CTH M | STH 16 | Nelson Road | 3 | 2023 | 220000 |  | Rural Section & Safety Project Design |  | 220000
CTH I | CTH M | CTH II | 4 | 2023 | 1163389 | 1.84 | Rural Section & Safety Project |  | 1163389
CTH XX | STH 35 | CTH OT | 3 | 2023 | 3860895 | 5.9 | Rural Section & Safety Project | 1500000 | 2360895 |  | Indian Reservation Roads
CTH M | STH 16 | Nelson Road | 3 | 2024 | 2180000 | 3.484 | Rural Section & Safety Project |  | 2180000
CTH M | CTH O | CTH I | 3 | 2024 | 560000 |  | Rural Design and Safety |  | 560000
CTH JJ | STH 162 | CTH J | 2 | 2024 | 1086435 | 2.04 | Rural Section |  | 1086435
CTH M | CTH O | CTH I | 3 & 4 | 2025 | 5560000 | 2.65 | Rural Section & Safety Project | 3720034 | 1839966 |  | STP Rural
CTH B | CTH J | CTH U | 3 & 2 | 2025 | 1170000 | 3.86 | Rural Section |  | 1170000
CTH H | CTH G | Monroe Cnty line | 4, 3 & 2 | 2025 | 871940 | 3.25 | Rural Section |  | 871940
CTH J | CTH U | I90 | 4 |  | 403247 | 0.61 | Urban Section |  | 403247
CTH YY | STH 33 | CTH M | 3 & 6 |  | 3054196 | 4.345 | Rural Section & Safety Project |  | 3054196
CTH J | Jernander Road | Kirking Road | 3 |  | 2755861 | 3.83 | Rural Section & Safety Project |  | 2755861
CTH I | CTH II | 33 | 4 |  | 4434678 | 3.691 | Rural Section & Safety Project |  | 4434678
CTH DE | STH 16 | Balmer Road | 2 & 4 |  | 4584299 | 2.91 | Rural Section & Safety Project |  | 4584299
CTH W | CTH D | CTH D | 4 |  | 5289716 | 6.02 | Rural Section & Safety Project |  | 5289716
CTH E | CTH DE | McRae Rd | 4 |  | 276990 | 0.81 | Rural Section |  | 276990
CTH X | CTH P | Monroe Cnty line | 3 |  | 402434 | 1.5 | Rural Section |  | 402434
CTH D | CTH M | CTH M | 4 |  | 55731 | 0.04 | Rural Section |  | 55731
CTH VV | CTH T | Lockington Rd. | 4 |  | 877306 | 3.27 | Rural Section |  | 877306
CTH DE | STH 108 | CTH E | 3 |  | 630000 | 2.84 | Rural Section |  | 630000
CTH M | Valley View Road | STH 33 | 3 & 4 |  | 1483638 | 5.53 | Rural Section |  | 1483638
CTH M | J O Johnson | CTH D | 3 & 4 |  | 1148277 | 4.28 | Rural Section |  | 1148277
CTH P | Pinske Ln | Endcott Dr. | 4 |  | 638528 | 2.38 | Rural Section |  | 638528
CTH D | William Ct. | CTH W | 4 |  | 2226799 | 8.3 | Rural Section |  | 2226799
CTH Y | CTH J | Monroe Cnty line | 3 |  | 407800 | 1.52 | Rural Section |  | 407800
CTH H | Erickson Lane | CTH G | 3 |  | 458775 | 1.71 | Rural Section |  | 458775
CTH NN | CTH M | STH 162 | 4 |  | 842429 | 3.14 | Rural Section |  | 842429
CTH OT | STH 35 | STH 35 | 3 |  | 543907 | 1.45 | Rural/Urban Section |  | 543907
CTH ZM | CTH Z | CTH OT | 3 |  | 187554 | 0.5 | Rural Section |  | 187554
CTH ZN | CTH ZZ | CTH OT | 4 |  | 945272 | 2.52 | Rural Section |  | 945272
CTH M | CTH I | Malzacher Rd | 3 & 4 |  | 589854 |  | Design |  | 589854
CTH M | CTH I | Malzacher Rd | 3 & 4 |  | 3932357 | 2.241 | Rural Section | 3145886 | 786471 |  | STP Rural
CTH S | CTH SN | CTH M | 4 |  | 3379759 | 2.629 | Rural Section |  | 3379759
|  |  |  | Total | 66350189 | 97.13 |  | 10764405 | 55585784 | 0
Small Bridge Work (<20 foot span) Work
Structure # | Road | Feature Crossing |  | Scheduled Year | Budget Cost | Deck Area | Notes | Grant | County Cost | Others Cost | Other Info
Culvert | CTH M/W | Jostad Coulee |  | 2022 | 140000 | 616 |  |  | 140000 | 0
Culvert | CTH E | BR Burns Creek |  | 2022 | 150000 | 300 |  |  | 150000
697-1 | CTH Q | Br German Valley |  | 2022 | 150000 | 400 |  |  | 150000
696-1R | CTH Q | Br German Valley |  | 2024 | 400000 | 320 |  |  | 400000
|  |  |  | Total | 840000 | 1636 |  | 0 | 840000 | 0
Bridge Design and Construction
Structure # | Road | Feature Crossing | Bridge Rating | Scheduled Year | Budget Cost | Deck Area in sq. ft | Notes | Grant | County Cost | Others Cost | Other Info
B320004 | CTH M | La Crosse River | 35.9 | 2021 | 333950 | 6837 | Design | 267160 | 66790
P320100 | CTH M | Halfway Creek | 40.4 | 2021 | 435840 | 864 | Construction | 348672 | 87168
P320923 | Mohican Road | Br. Sand Lake Coulee | 50.9 | 2022 | 71125 | 1027 | Design |  | 35563 | 35562
P320055 | CTH D | Halfway Creek | 48.7 | 2022 | 725600 | 1814 | Construction | 607672 | 117928 |  | Posted 25 Ton
B320004 | CTH M | La Crosse River | 35.9 | 2023 | 2658325 | 6837 | Construction | 2126660 | 531665
B320007 | CTH M | Bostwick Creek | 52.6 | 2024 | 192700 | 1927 | Design |  | 192700
B320019 | CTH M | Larson Coulee Crk | 59.3 | 2024 | 96300 | 963 | Design |  | 96300
B320020 | CTH O | Bostwick Creek | 53 | 2024 | 297700 | 2977 | Design |  | 297700
P320923 | Mohican Road | Br. Sand Lake Coulee | 50.9 | 2025 | 410800 | 1027 | Construction | 328640 | 41080 | 41080
B320014 | CTH M | Russian Coulee Creek | 49.2 | 2025 | 658800 | 1647 | Construction | 527040 | 131760
B320007 | CTH M | Bostwick Creek | 52.6 | 2025 | 770800 | 1927 | Construction | 616640 | 154160
B320548 | CTH M | Fleming Creek | 56.7 |  | 284500 | 2845 | Design |  | 284500
P320903 | Drogseth Rd | Bostwick Creek | 44.9 |  | 307200 | 768 | Construction | 245760 | 30720 | 30720
B320020 | CTH O | Bostwick Creek | 53 |  | 1190800 | 2977 | Construction | 952640 | 238160
B320019 | CTH M | Larson Coulee Crk | 60 |  | 385200 | 963 | Construction | 308160 | 77040
B320548 | CTH M | Fleming Creek | 56.7 |  | 1138000 | 2845 | Construction | 910400 | 227600
B320050 | CTH G | Coon Creek | 46 |  | 175350 | 2505 | Design |  | 175350 |  | Posted 20 Ton
P320095 | CTH V | Sour Creek | 93.3 |  | 113820 | 1626 | Design |  | 113820 |  | Posted 25 Ton
P320126 | Knudson Road | Halfway Creek | 68.9 |  | 88060 | 1258 | Design |  | 44030 | 44030 | Posted 20 Ton
P320163 | Drectah Road | Garbers Coulee Creek | 86.3 |  | 145460 | 2078 | Design |  | 72730 | 72730 | Posted 30 Ton
P320175 | Breidel Coulee Rd | Br. Mormon Creek | 75 |  | 79030 | 1129 | Design |  | 39515 | 39515 | Posted 20 Ton
P320910 | Muenzenberger Rd | Coon Creek | 70.8 |  | 34160 | 488 | Design |  | 17080 | 17080 | Posted 15 Ton
B320050 | CTH G | Coon Creek | 46 |  | 701400 | 2505 | Construction | 561120 | 140280 |  | Posted 20 Ton
P320095 | CTH V | Sour Creek | 93.3 |  | 455280 | 1626 | Construction | 364224 | 91056 |  | Posted 25 Ton
P320126 | Knudson Road | Halfway Creek | 68.9 |  | 352240 | 1258 | Construction | 281792 | 35224 | 35224 | Posted 20 Ton
P320163 | Drectah Road | Garbers Coulee Creek | 86.3 |  | 581840 | 2078 | Construction | 465472 | 58184 | 58184 | Posted 30 Ton
P320175 | Breidel Coulee Rd | Br. Mormon Creek | 75 |  | 316120 | 1129 | Construction | 252896 | 31612 | 31612 | Posted 20 Ton
P320910 | Muenzenberger Rd | Coon Creek | 70.8 |  | 136640 | 488 | Construction | 109312 | 13664 | 13664 | Posted 15 Ton
|  |  |  | Total | 13137040 | 56413 |  | 9274260 | 3443379 | 419401
Other Major Maintenance Projects - mainly Storm Water
Road | From | To | Paser Rating | Scheduled Year | Budget Cost Construction | Mileage | Notes | Grant | County Cost | Others Cost | Other Info
Brice's Prairie |  |  | n/a | 2024 | 248000 | 13.87 | Design |  | 248000
CTH Z | STH 35 | Termini | 6 |  | 293542 | 6.19 | Storm Water Proj. |  | 293542
CTH ZB | CTH Z | CTH Z | 7 |  | 298283 | 3.37 | Storm Water Proj. |  | 298283
CTH ZB-2 | CTH ZB | CTH ZN | 7 |  | 60546 | 0.25 | Storm Water Proj. |  | 60546
CTH ZM | CTH Z | CTH OT | 6 |  | 121094 | 0.5 | Storm Water Proj. |  | 121094
CTH ZN | CTH ZB | Front St. | 7 |  | 139284 | 2.91 | Storm Water Proj. |  | 139284
CTH ZZ | CTH ZN | CTH Z | 8 |  | 134544 | 0.65 | Storm Water Proj. |  | 134544
|  |  |  | Total | 1295293 | 27.74 |  | 0 | 1295293 | 0
Majors & Enhancements
Road | From | To | Paser Rating | Scheduled Year | Budget Cost Construction | Mileage | Notes | Grant | County Cost | Others Cost | Other Info
CTH B | CTH BW | I90 Ramp | 3 | 2021 | 311908.01 |  | Urban Section Design |  | 311908.01
CTH B | I90 Ramp | Clinton St. | 4 | 2021 | 500000 |  | Urban Section Design |  | 500000
CTH B | STH 162 | I90 | 2 & 3 | 2021 | 1220575 | 0.9 | Urban Section | 672073 | 548502 |  | CDBG Close
CTH SN | Hanson Road | Alpine Ln. | 3 & 4 | 2021 | 3212790 | 1.29 | Urban Section Reconstruction | 2124247 | 945743 | 142800 | STP-Urban/Holmen
CTH OT/Commerce |  | Intersection Improv. | n/a | 2021 | 275000 |  | Intersection Design |  | 275000
CTH OT/Commerce |  | Intersection Improv. | n/a | 2022 | 475000 |  | Intersection Real Estate |  | 475000
CTH B | CTH BW | I90 Ramp | 3 | 2025 | 4623000 | 0.75 | Urban Section | 3698400 | 924600 |  | STP-Urban
CTH B | I90 Ramp | Clinton St. | 4 | 2028 | 5977000 | 1.32 | Urban Section | 4781600 | 1195400 |  | STP-Urban
CTH OT/Commerce |  | Intersection Improv. | n/a |  | 1200000 |  | Intersection Improv. |  | 1200000
CTH OT/XX |  | Intersection Improv. | n/a |  | 1100000 |  | Intersection Improvement Safety |  | 1100000
CTH B/O |  | Intersection Improv. | n/a |  | 250000 |  | Intersection Improvement |  | 250000
CTH B/U |  | Intersection Improv. | n/a |  | 300000 |  | Intersection Improvement |  | 300000
CTH C | Buol Rd | Garland St | 3 & 4 |  | 1291421 | 0.6 | Part Urban w/overpass |  | 1291421
CTH D | Main St. | Willann Ct. | 4 |  | 538092 | 0.25 | Urban Section Widen to 3 lanes |  | 538092
CTH D/DH |  | Intersection Improv. | n/a |  | 45000 |  | Intersection Improvement |  | 45000
CTH M/B |  | Intersection Improv. | n/a |  | 25000 |  | Intersection Improvement |  | 25000
CTH M/C |  | Intersection Improv. | n/a |  | 300000 |  | Intersection Improvement |  | 300000
CTH MH | STH 53 | CTH HD | n/a |  | 600000 | 1.246 | Access Control |  | 600000
CTH N & CTH O |  | Access Control | n/a |  | 25000 |  | Access Control |  | 25000
CTH OT | STH 35 | CTH XX | 3 |  | 400000 | 0.64 | Urban Section |  | 400000
CTH BW | Hinkley Road | Airport Road | 4 |  | 4369310 | 2.03 | Urban Section |  | 4369310
CTH HD | CTH MH | STH 35 | 4 |  | 2000732 | 2.051 | Urban/Rural Section Rehab |  | 2000732
CTH OT | STH 35 | CTH SN | 4 |  | 2140000 | 0.76 | Urban Section |  | 2140000
|  |  |  | Total | 31179828.01 | 11.837 |  | 11276320 | 19760708.01 | 142800
Resurfacing/Maintenance Overlays
Road | From | To | Paser Rating | Scheduled Year | Budget Cost Construction | Mileage | Notes | Grant | County Cost | Others Cost | Other Info
CTH E | STH 162 North | McCrae Road | 6 |  | 295000 | 2.95 | Improved 1998 |  | 295000
CTH JB | STH 33 | STH 162 | 6 |  | 299000 | 2.99 | Improved 1998 |  | 299000
CTH DE | CTH C | STH 108 | 6 |  | 206000 | 2.06 | Improved 2002 |  | 206000
CTH ZB-2 | CTH ZB | CTH ZN | 5 |  | 25000 | 0.25 | Improved 1968 |  | 25000
CTH ZM | CTH Z | CTH OT | 6 |  | 50000 | 0.5 | Improved 1988 |  | 50000
CTH ZB | CTH Z | CTH Z | 7 |  | 337000 | 3.37 | Improved 2007 |  | 337000
CTH ZN | CTH ZB | Front St. | 7 |  | 291000 | 2.91 | Improved 2008 |  | 291000
CTH ZZ | CTH ZN | CTH Z | 7 |  | 65000 | 0.65 | Improved 2008 |  | 65000
CTH FO | CTH OA | CTH F | 7 |  | 185000 | 1.85 | Improved 2004 |  | 185000
CTH F | STH 33 | Briarwood Avenue | 7 |  | 310000 | 3.1 | Improved 2004 |  | 310000
CTH FA | CTH F | Cul-de-sac | 7 |  | 169300 | 1.693 | Improved 2006 |  | 169300
CTH K | STH 35 | County Line | 7 |  | 78000 | 0.78 | Improved 1997 |  | 78000
CTH II | STH 162 | CTH I | 7 |  | 411000 | 4.11 | Improved 2006 |  | 411000
CTH G | CTH H | Muenzenberger Road | 7 |  | 664000 | 6.64 | Improved 1999 |  | 664000
CTH D | STH 108 | Hall Road | 7 |  | 409000 | 4.09 | Improved 2003 |  | 409000
CTH D | Hall Road | CTH W | 7 |  | 444000 | 4.44 | Improved 2004 |  | 444000
CTH T | STH 53 | Wm Severson Road | 7 |  | 500000 | 5 | Improved 2005 |  | 500000
CTH T | STH 108 | Wm Severson Road | 7 |  | 542000 | 5.42 | Improved 1999 |  | 542000
|  |  |  | Total | 5280300 | 52.803 |  | 0 | 5280300 | 0
Capital Facility Projects | Scheduled Year
Midway Building Upgrade |  |  |  |  | 875276 |  |  |  | 875276
West Salem HVAC Upgrade |  |  |  |  | 350000 |  |  |  | 350000
West Salem Truck Shop Design |  |  |  |  | 349940 |  |  |  | 349940
West Salem Truck Shop Construction |  |  |  |  | 4116932 |  |  |  | 4116932
West Salem Tent Re-Covering |  |  |  |  | 70000 |  |  |  | 70000
Mindoro Shop Site |  |  |  |  | 150000 |  |  |  | 150000
St Joseph Shop Buildings - Phase 2 |  |  |  |  | 1809870 |  |  |  | 1809870
St Joseph Shop Buildings - Phase 1 | 2021 |  |  |  | 4200000 |  |  |  | 4200000
|  |  |  | Total | 11922018 |  |  | 0 | 11922018 | 0
|  |  | Total |  | 130004668.01 |  |  | 31314985 | 98127482.01 | 562201
|  |  | TOTALS |  |  |  | County | Grant | Others
|  |  |  | TOTAL 2021 | 13387018.01 |  | 9559471.01 | 3684747 | 142800
|  |  |  | TOTAL 2022 | 7792893 |  | 5023769 | 2733562 | 35562
|  |  |  | TOTAL 2023 | 9052609 |  | 5425949 | 3626660 | 0
|  |  |  | TOTAL 2024 | 5061135 |  | 5061135 | 0 | 0
|  |  |  | TOTAL 2025 | 14065340 |  | 5133506 | 8890754 | 41080
|  |  |  | Unscheduled | 80645673 |  | 67923652 | 12379262 | 342759
|  |  |  | TOTAL | 130004668.01 |  | 98127482.01 | 31314985 | 562201
Projects For 2021
Road/Structure # | From | To | Notes | Paser Rating | Mileage | Bridge Rating | Surface in Square Feet | Budget Cost | County Cost | Grant | Others Cost
CTH TA | CTH T | CTH A | Rural Section | 2 | 2.69 |  |  | 1354657 | 1354657 | 0 | 0
Concrete Driveways |  |  | Construction |  |  |  |  | 50000 | 50000 | 0 | 0
CTH YY | STH 14 | STH 33 | Rural Section & Safety Project | 3 | 3.59 |  |  | 1492298 | 1219703 | 272595 | 0
B320004 | CTH M | La Crosse River | Design |  |  | 35.9 | 6837 | 333950 | 66790 | 267160 | 0
P320100 | CTH M | Halfway Creek | Construction |  |  | 40.4 | 864 | 435840 | 87168 | 348672 | 0
CTH B | CTH BW | I90 Ramp | Urban Section Design | 3 |  |  |  | 311908.01 | 311908.01 | 0 | 0
CTH B | I90 Ramp | Clinton St. | Urban Section Design | 4 |  |  |  | 500000 | 500000 | 0 | 0
CTH B | STH 162 | I90 | Urban Section | 2 & 3 | 0.9 |  |  | 1220575 | 548502 | 672073 | 0
CTH SN | Hanson Road | Alpine Ln. | Urban Section | 3 & 4 | 1.29 |  |  | 3212790 | 945743 | 2124247 | 142800
CTH OT/Commerce |  | Intersection Improv. | Intersection Improv. |  |  |  |  | 275000 | 275000 | 0 | 0
- | [7 empty] | 0 | 0 | 0 | 0
St Joseph Shop Buildings - Phase 1 | [7 empty] | 4200000 | 4200000 | 0 | 0
|  |  |  | Total | 8.47 |  |  | 13387018.01 | 9559471.01 | 3684747 | 142800

## Town Bridges (hidden)
Town Bridge Work
Structure # | Road | Feature Crossing | Bridge Rating | Scheduled Year | Budget Cost | Deck Area | Notes | Grant | County Cost | Others Cost
P320903 | DROGSETH RD | BOSTWICK CREEK | 44.9 | 2016 | 107520 | 768 ft | Local Bridge Program/Bridge & Culvert Aid | 86016 | 10752 | 10752
|  |  |  | Total | 107520 |  |  | 86016 | 10752 | 10752

## Maintenance (hidden)
CTH Q | CTH V | STH 108 | 6 | 2013 |  | 5.51 | Seal Coating
CTH J | STH 16 | CTH Y | 6 | 2013 |  | 3.8 | Seal Coating
CTH U | CTH B | CTH J | 4 | 2013 |  | 3.29 | Seal Coating
CTH A | STH 108 | CTH C |  |  |  |  | Shouldering
CTH E | STH 162 | STH 16 |  |  |  |  | Shouldering
CTH II | STH 162 | CTH I |  |  |  |  | Shouldering
CTH YY | STH 14 | STH 33 |  | 2014 |  |  | Shouldering
CTH MM | STH 14 | STH 14 |  | 2014 |  |  | Shouldering
CTH N | STH 162 | County Line |  |  |  |  | Shouldering
CTH M | STH 14 | STH 33 |  |  |  |  | Shouldering
CTH F | STH 33 | Briarwood Avenue |  |  |  |  | Shouldering
CTH FA | CTH F | Cul de sac |  |  |  |  | Shouldering
CTH U | CTH J | CTH B |  |  |  |  | Shouldering
CTH V | CTH T | CTH Q |  |  |  |  | Shouldering
All CTHs | County Wide | Crackfilling | n/a | Every year | 300000 |  | Crackfilling
Various CTHS | County Wide | Sealcoating | n/a | Every year | 460000 | 20 | Sealcoating
Various CTHS | County Wide | Shouldering | n/a | Every year | 240000 | 30 | Shouldering
All CTHs | County Wide | Sign upgrade | n/a | 2013 | 78474 |  | Sign upgrade | 78474

## Project Problems (hidden)
CTH XX
Curve supers deficient south of Dummer farm?
CTH HD
Turning lane Bluff View Ct.

## Resurfacing (hidden)
Resurfacing/Maintenance Overlays
Road | From | To | Paser Rating | Scheduled Year | Budget Cost Construction | Mileage | Notes | Grant | County Cost | Others Cost
CTH E | STH 162 North | McCrae Road | 6 | 2013 | 295000 | 2.95 | Improved 1998 |  | 295000
CTH JB | STH 33 | STH 162 | 6 | 2013 | 299000 | 2.99 | Improved 1998 |  | 299000
CTH NN | CTH M | STH 162 | 6 | 2013 | 314000 | 3.14 | Improved 1998 |  | 314000
CTH DE | CTH C | STH 108 | 6 | 2014 | 206000 | 2.06 | Improved 2002 |  | 206000
CTH ZB2 | CTH ZB | CTH ZN | 5 | 2014 | 25000 | 0.25 | Improved 1968 |  | 25000
CTH ZM | CTH Z | CTH OT | 6 | 2014 | 50000 | 0.5 | Improved 1988 |  | 50000
CTH Z | STH 35 | Termini | 6 | 2015 | 619000 | 6.19 | Improved 1998 |  | 369000 | 250000 | IRR Funding
CTH ZB | CTH Z | CTH Z | 7 | 2015 | 337000 | 3.37 | Improved 2007 |  | 337000
CTH ZN | CTH ZB | Front St. | 7 | 2015 | 291000 | 2.91 | Improved 2008 |  | 291000
CTH ZZ | CTH ZN | CTH Z | 7 | 2015 | 65000 | 0.65 | Improved 2008 |  | 65000
CTH FO | CTH OA | CTH F | 7 | 2015 | 185000 | 1.85 | Improved 2004 |  | 185000
CTH F | STH 33 | Briarwood Avenue | 7 | 2015 | 310000 | 3.1 | Improved 2004 |  | 310000
CTH FA | CTH F | Culdesac | 7 | 2015 | 169300 | 1.693 | Improved 2006 |  | 169300
CTH K | STH 35 | County Line | 7 | 2016 | 78000 | 0.78 | Improved 1997 |  | 78000
CTH II | STH 162 | CTH I | 7 | 2016 | 411000 | 4.11 | Improved 2006 |  | 411000
CTH G | CTH H | Muenzenberger Road | 7 | 2016 | 664000 | 6.64 | Improved 1999 |  | 664000
CTH D | STH 108 | Hall Road | 7 | 2017 | 409000 | 4.09 | Improved 2003 |  | 409000
CTH D | Hall Road | CTH W | 7 | 2017 | 444000 | 4.44 | Improved 2004 |  | 444000
CTH T | STH 53 | Wm Severson Road | 7 | 2018 | 500000 | 5 | Improved 2005 |  | 500000
CTH T | STH 108 | Wm Severson Road | 7 | 2018 | 542000 | 5.42 | Improved 1999 |  | 542000
|  |  |  | Total | 6213300 | 62.133 |  |  | 5963300